## CoAX 2002
CoAX TIE Status
Organization | TIE With | TIE Purpose | Lead | Status | Interaction Codes:
AIAI | Michigan | IX-CFC invokes MCA | Austin Tate | done | 01
| GITI | IX-CFMCC receives messages and changes I-Space | Austin Tate | done | 02
| BBN | IX-Arabello-HQ created and changes I-Space | Austin Tate | done | 03
| UTexas | IX-CFC invokes AAO | Austin Tate | done | 04
| Dartmouth/IHMC | IX-Australia-HQ (1) initiation of attack and (2) notification of the need for a medevac | Austin Tate | done | 05
| QinetiQ | IX-CFC receives and sends various messages | Austin Tate | done | 06
| UMD | IX-US-HQ invokes UMD-Predict with various parameters. | Austin Tate | done | 07
|  | (Plus Jeff Dalton) |  |  | 08
09
10
BBN (Arabello) | CMU | (1) Use of Matchmaker for DAML-S | Mark Burstein | (1) done | 11
| CMU | (2) Policies for controlling access to Matchmaker | " | (2) TBD | 12
| IHMC | Content Policy Enforcer | " | In Progress | 13
| AIAI | Evaluation of new country tailoring of an I-X Process Panel - IX-Arabello-HQ | " | done | 14
| LM | Information Broker utilization for wizard in Agent Toolkit | " | done | 15
| QinetiQ | Simulating, Time Keeper | Dave Diller, Brett Benyo | done | 16
| NRL | Display other maritime entities | " | In Progress | 17
| UTexas | Data for other sensors; content of analysis of Arabello role | " | TBD | 18
19
20
CMU (Coalition / SysAdmin) | BBN | Matchmaker Content | Jo Giampapa | In Progress | 21
| IHMC | Policies - Getting notification of agents joining for usage by the visualizer) | " | In Progress | 22
| All | Anaconda Visualiser | " | In Progress | 23
|  | (Plus Sean Owen) |  |  | 24
25
Dartmouth | IHMC, AIAI | IX-CFMCC links to IX-Australia-HQ and IX-CFC | Bob Gray | In Progress | 26
27
28
29
30
DSTO (Australia HQ) | AIAI | Australian panel | Steve Wark | In Progress | 31
| Dartmouth / IHMC | Medical montoring agents | " | In Progress | 32
| UMICH | Medevac deconfliction | " | In Progress | 33
| Self | Medevac plan | " | In Progress | 34
35
GITI (Maritime) | AIAI | Install IX-CFMCC | Dennis Brake | done | 36
| IHMC | Security Enhancements with the Grid | IHMC | done | 37
| NRL | XIS display in Verona | Dennis Brake | testing | 38
|  | (Plus Ray Emami) |  |  | 39
40
IHMC (SysAdmin) | Dartmouth, AIAI | Australian Ship Medevac | Niranjan Suri | In Progress | 41
| GITI | Security enhancements with Grid | Renia Jeffers |  | 42
| BBN | Content policy enforce | Jeff Bradshaw |  | 43
| CMU | Policies/visualization and matchmaking content | " |  | 44
|  | (Plus Jeff Bradshaw, Renia Jeffers, Maggie Breedy, Andrzej Uszok) |  |  | 45
LM-ATL (US HQ) | BBN | (1) integrate BBN Wizard into LM toolkit | Chris Garrett | (1) Complete | 46
| BBN | (2) receive DAML format data from Arabello | " | (2) Nearly Complete | 47
| IHMC | Make LM agent KAOS aware | " | got sample instructions | 48
| UTexas | Send Arabello ASW data (translate into XML) | Martin Hofmann | got exact formats; waiting for test client | 49
| AIAI | Install IX-US-HQ | " | done | 50
| UMD | Install IMPACT software data on USHQ PC | " | done | 51
| DSTO / IHMC / Dartmouth | Recieve medevac reports | " |  | 52
|  | (Plus Axel Anaruk) |  |  | 53
54
55
NRL (Maritime) | QinetiQ | Show something unique, potentially alerts for one another | Ranjeev Mittu | TBD | 56
| GITI | Integrate NRL C2 System in CFMC display | " | In Progress | 57
| Utexas | Accept Merged ASW report in NRL System | " | Interface done | 58
| UMD | Receive Prediction Matrix | " | Interface done | 59
| BBN | Receive Maritime entities with regard to Coalition | " | TBD as BBN completes scenario | 60
|  | (Plus Frank Segaria and Suleyman Guleyupoglu) |  |  | 61
62
63
64
65
Potomac Institute | DARPA | Collecting video material appropriate for the scenario. | Patrick Worcester | In Progress | 66
|  | Editing the CoAX intro video with Will Sands Voice-over | " | In Progress | 67
|  | Editing the MNN videos 01 - 03 for use during the demo | " | In Progress | 68
69
70
QinetiQ (Coalition) | NRL | Agree displays, maybe exchange alerts | Dave Allsopp | To do | 71
| UMD | Display predictions on Decision Desktop | " | basic testing ok | 72
| AIAI | Run IX-CFC | AIAI | basic testing ok | 73
| UTexas | Display sensor information on Decision Desktop | Dave Allsopp | basic testing ok | 74
| BBN | Coordinate on simulation and time server | " | In Progress | 75
|  | (Plus Patrick Beautement) |  |  | 76
77
78
79
80
UMD | AIAI | IX-US-HQ invokes UMD-Predict with various parameters. | Robert Ross | Installed on laptop | 81
| NRL | Provides tracking information and receives prediction matrices. | " | Comm done | 82
| QinetiQ | Provides Intelligence information and receives prediction Windows | " | Comm done | 83
| UTexas | Provides Tracking information | " | Comm done | 84
85
UMichigan (Coalition) | AIAI | Invoke/report deconfliction/coordination from IX-CFC | Ed Durfee | Essentially done (KAoS flaky) | 86
| DSTO? | Receive medevac plans? | " | New -- far from done | 87
|  | (Plus Jeff Cox anf Thom Bartold) |  |  | 88
89
90
UTexas (US HQ) | BBN | Matchmaker (arabello Feed) -- issues about content) | BBN | (1) Matchmaker may or may not be used (TBD), (2) BBN generating Arabello simulation feed | 91
| UMD | Feed "merged" sensor report to UMD | Tom Graser | testing | 92
| QinetiQ | Display "merged" sensor report on Decision Desktop | " | testing | 93
| AIAI | Send AAO Activity Request from IX-CFC | " | Testing Complete | 94
| LM | Translate Arabello DAML to XML | " | LM has format and is coding | 95
| NRL | Display "merged" sensor report on NRL Display | " | NRL ready to test | 96
|  | (Plus Suzanne Barber and Ryan McKay) |  |  | 97
98
99
100
Miscellaneous |  |  |  |  | 101
102
103
104
105
106
107
108
109
110